## Resources
Partners | PIC | (1) partner direct personnel monthly rate |  |  | Instructions
LJMU | 998079949
Loughborough | 999990752 | 6800 |  |  | (1) enter personnel monthly rate
Oslo | 999975814 | 7821.8496 |  |  | (2) enter PM in PM per task sheet
OULU | 999844670 | 8000 |  |  | (3) enter other cost in other direct cost sheet
PISA | 999862712 | 6650 |  |  | (4) enter subcontracting cost (justify) in subcontracting sheet
TRENTO | 999841954 | 6650 |  |  | (5) enter travel cost in travel sheet
Groningen | 999989782 | 6900
Glasgow | 999974165 | 6908
RWTH | 999591112 | 7000
Fraunhofer | 999984059 | 8968.36
Vicomtech | 955552336 | 5260
Beyond Vision | 912509847 | 4000
Intracom | 999969994 | 5700
7bulls | 919795129 | 7000
Telefonica | 917790915 | 7680
Trialog | 999617884 | 8500
ATC | 999751744 | 5500
Liv5G | 865996989 | 7360
IDSA | 919489191 | 9000
FORTH | 999995893 | 6000
AI Invest | 899809443 | 7000
SWISS SMART | 909553093 | 10850
DEXAI | 888937586 | 7500
ITG | 991720047 | 4500
Koblenz | 999856407 | 8968.36
8BELLS | 917066131 | 5500
This table will be used in proposal
Number | Partners | WP1 | WP2 | WP3 | WP4 | WP5 | WP6 | WP7 | WP8 | Total | Persons/year
1 | LJMU | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Loughborough | 6 | 4 | 40 | 46 | 0 | 0 | 9 | 5 | 110 | 2.8205
3 | Oslo | 5 | 7 | 30 | 48 | 0 | 17 | 0 | 6 | 113 | 2.8974
4 | OULU | 0 | 4 | 18 | 18 | 0 | 0 | 18 | 4 | 62 | 1.5897
5 | PISA | 5 | 8 | 0 | 0 | 35 | 0 | 6 | 5 | 59 | 1.5128
6 | TRENTO | 5 | 8 | 0 | 36 | 6 | 8 | 0 | 5 | 68 | 1.7436
7 | Groningen | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 4 | 58 | 1.4872
8 | Glasgow | 0 | 3 | 0 | 0 | 53 | 41 | 0 | 7 | 104 | 2.6667
9 | RWTH | 0 | 48 | 0 | 3 | 0 | 0 | 22 | 7 | 80 | 2.0513
10 | Fraunhofer | 9 | 24.5 | 0 | 0 | 29 | 0 | 0 | 24 | 86.5 | 2.2179
11 | Vicomtech | 2 | 15 | 10 | 10 | 0 | 0 | 33 | 4 | 74 | 1.8974
12 | Beyond Vision | 3.5 | 17 | 4 | 5 | 2 | 0 | 42 | 5.5 | 79 | 2.0256
13 | Intracom | 5 | 10 | 0 | 6 | 8 | 48 | 29 | 8 | 114 | 2.9231
14 | 7bulls | 7 | 8 | 0 | 2 | 3 | 22 | 34 | 14 | 90 | 2.3077
15 | Telefonica | 7 | 6 | 15 | 30 | 15 | 0 | 0 | 12 | 85 | 2.1795
16 | Trialog | 4 | 20 | 0 | 13 | 17 | 0 | 25 | 14 | 93 | 2.3846
17 | ATC | 0 | 10 | 0 | 0 | 20 | 39 | 0 | 25 | 94 | 2.4103
18 | Liv5G | 0 | 2 | 5 | 0 | 22 | 0 | 23 | 4 | 56 | 1.4359
19 | IDSA | 3 | 0 | 0 | 14 | 0 | 0 | 0 | 18 | 35 | 0.89744
20 | FORTH | 1 | 6 | 29 | 4 | 10 | 5 | 12 | 8 | 75 | 1.9231
21 | AI Invest | 3 | 15 | 0 | 0 | 3 | 5 | 23 | 2 | 51 | 1.3077
22 | SWISS SMART | 2 | 3 | 40 | 0 | 3 | 8 | 20 | 2 | 78 | 2
23 | DEXAI | 10 | 6 | 0 | 0 | 48 | 0 | 10 | 4 | 78 | 2
24 | ITG | 5 | 25.5 | 0 | 3 | 0 | 0 | 44 | 2.5 | 80 | 2.0513
25 | Koblenz | 9 | 24.5 | 0 | 0 | 29 | 0 | 0 | 24 | 86.5 | 2.2179
26 | 8BELLS | 1 | 3 | 0 | 0 | 0 | 26 | 18 | 32 | 80 | 2.0513
|  | 92.5 | 331.5 | 191 | 238 | 303 | 219 | 368 | 246 | 1989 | 48.9487
This table will be used in proposal
Number | Partners | PM cost | (2) Other cost | (3) subcontracting cost | Total Direct Cost | Total indirect cost | Total budget | Funding rate | Total funding | PM | TYPE | Country | Role
1 | LJMU | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0 | 0 | university | UK |  |  | Funding | PM
2 | Loughborough | 748000 | 92560 | 0 | 840560 | 210140 | 1050700 | 100% | 1050700 | 110 | university | UK |  | UK | 13.38% | 13.57%
3 | Oslo | 883869 | 90960.8794 | 0 | 974829.8794 | 243707.4698 | 1218537.3492 | 100% | 1218537.3492 | 113 | university | Norway |  | Norway | 6.17% | 5.681%
4 | OULU | 496000 | 104000 | 60000 | 660000 | 150000 | 810000 | 100% | 810000 | 62 | university | Finland |  | Finland | 4.101% | 3.117%
5 | PISA | 392350 | 79000 | 0 | 471350 | 117837.5 | 589187.5 | 100% | 589187.5 | 59 | university | Itlay |  | Itlay | 10.2% | 10.31%
6 | TRENTO | 452200 | 65000 | 0 | 517200 | 129300 | 646500 | 100% | 646500 | 68 | university | Itlay |  | Netherlands | 2.761% | 2.916%
7 | Groningen | 400200 | 36000 | 0 | 436200 | 109050 | 545250 | 100% | 545250 | 58 | university | Netherlands |  | Germany | 17.87% | 14.48%
8 | Glasgow | 673894 | 54000 | 0 | 727894 | 181973.5 | 909867.5 | 100% | 909867.5 | 104 | university | UK |  | Spain | 10.46% | 12.02%
9 | RWTH | 560000 | 144000 | 0 | 704000 | 176000 | 880000 | 100% | 880000 | 80 | Research Institution | Germany |  | Portugal | 2.571% | 3.972%
10 | Fraunhofer | 775763.14 | 94000 | 0 | 869763.14 | 217440.785 | 1087203.925 | 100% | 1087203.925 | 86.5 | Research Institution | Germany |  | Greece | 11.44% | 14.23%
11 | Vicomtech | 389240 | 79900 | 0 | 469140 | 117285 | 586425 | 100% | 586425 | 74 | Research Institution | Spain |  | Poland | 6.772% | 7.089%
12 | Beyond Vision | 316000 | 90200 | 0 | 406200 | 101550 | 507750 | 100% | 507750 | 79 | Industry | Portugal |  | Belgium | 0% | 0%
13 | Intracom | 649800 | 85700 | 0 | 735500 | 183875 | 919375 | 100% | 919375 | 114 | Industry | Greece |  | France | 5.357% | 4.676%
14 | 7bulls | 630000 | 44000 | 0 | 674000 | 168500 | 842500 | 100% | 842500 | 90 | Industry | Poland |  | Switzerland | 5.818% | 3.922%
15 | Telefonica | 652800 | 101000 | 0 | 753800 | 188450 | 942250 | 100% | 942250 | 85 | Industry | Spain
16 | Trialog | 790500 | 56000 | 0 | 846500 | 211625 | 1058125 | 100% | 1058125 | 93 | Industry | France |  |  | Funding | PM
17 | ATC | 517000 | 39000 | 0 | 556000 | 139000 | 695000 | 100% | 695000 | 94 | SME | Greece |  | university | 34.72% | 33.21%
18 | Liv5G | 412160 | 86000 | 60000 | 558160 | 124540 | 682700 | 100% | 682700 | 56 | Non-profit | UK |  | SME | 6.614% | 8.748%
19 | IDSA | 315000 | 64500 | 0 | 379500 | 94875 | 474375 | 100% | 474375 | 35 | Non-profit | Germany |  | Research Institution | 3.271% | 3.771%
20 | FORTH | 450000 | 66800 | 0 | 516800 | 129200 | 646000 | 100% | 646000 | 75 | Research Institution | Greece |  | Industry | 28.07% | 29.66%
21 | AI Invest | 357000 | 39000 | 0 | 396000 | 99000 | 495000 | 100% | 495000 | 51 | Industry | Poland |  | Non-profit | 14.4% | 12.52%
22 | SWISS SMART | 846300 | 73000 | 0 | 919300 | 229825 | 1149125 | 100% | 1149125 | 78 | Non-profit | Switzerland
23 | DEXAI | 585000 | 37500 | 0 | 622500 | 155625 | 778125 | 100% | 778125 | 78 | Industry | Itlay
24 | ITG | 360000 | 70400 | 0 | 430400 | 107600 | 538000 | 100% | 538000 | 80 | Non-profit | Spain
25 | Koblenz | 775763.14 | 94000 | 0 | 869763.14 | 217440.785 | 1087203.925 | 100% | 1087203.925 | 86.5 | university | Germany
26 | 8BELLS | 440000 | 49000 | 0 | 489000 | 122250 | 611250 | 100% | 611250 | 80 | SME | Cyprus
|  | 13868839.28 | 1786520.8794 | 120000 | 15335360.1594 | 3926090.0398 | 19750450.1992 |  | 19750450.1992 | 1989
Note on M60: ====== ID#AAAAs4-fjDM tc={E381881B-7F79-4DE5-8C4B-43C5185DE52F} (2023-03-14 17:56:02) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Attention. I think someone made a mistake when copying these country codes into this table. For instance, LIU is SE and not FR. LJMU is UK and not SE. etc.

## PM per task
This table is of internal use only
| Leader | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
WP1 – Project Management, Ethics & System Integration Governance (M1–M60) | LJMU | LJMU | LBORO | OSLO | OULU | PISA | TRENTO | GRONINGEN | GLASGOW | RWTH | FRAUNHOFER | VICOMTECH | BEYOND-VISION | INTRACOM | 7BULLS | TELEFONICA | TRIALOG | ATC | LIV5G | IDSA | FORTH | AI INVEST | SWISS SMART | DEXAI | ITG | Koblenz | 8BELLS
T1.1 Project Governance & Administrative Coordination (M1–M60) | LJMU |  | 2 | 2 |  |  | 2 |  |  |  | 2.5 | 1.5 | 1.5 | 2 | 2 | 2 | 1 |  |  | 1 | 1 | 1 |  | 1 | 2 | 2.5 | 1 | 28
T1.2 Technical Steering (M1–M60) | LJMU |  | 2 | 3 |  | 3 | 3 |  |  |  | 2.5 | 0.5 | 0.5 | 1 | 3 | 2 | 1 |  |  |  |  | 2 | 2 | 1 | 2 | 2.5 |  | 31
T1.3 Ethics, Legal & Regulatory Compliance Oversight (M1–M60) | DEX |  | 1 |  |  | 2 |  |  |  |  | 2 |  | 0.5 | 0 |  | 1 | 1 |  |  | 2 |  |  |  | 8 | 0.5 | 2 |  | 20
T1.4 Risk, Innovation & TRL Management (M1–M60) | LJMU |  | 1 | [7 empty] | 2 |  | 1 | 2 | 2 | 2 | 1 | [7 empty] | 0.5 | 2 |  | 13.5
|  | 0 | 6 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 9 | 2 | 3.5 | 5 | 7 | 7 | 4 | 0 | 0 | 3 | 1 | 3 | 2 | 10 | 5 | 9 | 1 | 92.5
WP2 – Conceptual Framework, Requirements & Reference Architecture (M1–M60) | Trialog | LJMU | LBORO | OSLO | OULU | PISA | TRENTO | GRONINGEN | GLASGOW | RWTH | FRAUNHOFER | VICOMTECH | BEYOND-VISION | INTRACOM | 7BULLS | TELEFONICA | TRIALOG | ATC | LIV5G | IDSA | FORTH | AI INVEST | SWISS SMART | DEXAI | ITG | Koblenz | 8BELLS
T2.1 Federated Self-Orchestrating AI Ecosystem Conceptual Framework (M1–M18) | Trialog |  |  | 2 | 1 | 2 | 3 |  | 1 | 3 | 3 | 1 | 1 | 2 | 2 | 1 | 3 | 5 |  |  | 1 | 1 |  | 2 | 1.5 | 3 |  | 38.5
T2.2 Use Case & ApplyAI Scenario Engineering (M1–M24) | AII |  | 2 |  | 1 | 2 | 2 |  | 1 |  | 4.5 | 6 | 4 | 2 | 2 | 1 | 3 |  |  |  | 2 | 10 | 1 | 2 | 2 | 4.5 | 2 | 54
T2.3 Functional & Non-Functional Requirements (M6–M30) | ITG |  |  |  | 1 | 2 |  |  |  |  | 7 | 6 | 6 | 2 | 2 | 1 | 3 |  |  |  | 2 | 2 |  | 2 | 21 | 7 |  | 64
T2.4 Reference Architecture Definition & Evolution (M6–M48) | FIR |  | 2 | 5 | 1 | 2 | 3 |  | 1 | 25 | 5 | 2 | 4 | 2 | 2 | 2 | 8 | 5 |  |  | 1 | 2 | 2 |  | 1 | 5 | 1 | 81
T2.5 Foundry Governance, Business & Marketplace Models (M12–M60) | UG | [6 empty] | 54 |  | 20 | 5 |  | 2 | 2 |  | 1 | 3 |  | 2 | [6 empty] | 5 |  | 94
|  | 0 | 4 | 7 | 4 | 8 | 8 | 54 | 3 | 48 | 24.5 | 15 | 17 | 10 | 8 | 6 | 20 | 10 | 2 | 0 | 6 | 15 | 3 | 6 | 25.5 | 24.5 | 3 | 331.5
WP3 – Cognitive Intelligence & Adaptive Learning Foundations (M1–M42) | SSF | LJMU | LBORO | OSLO | OULU | PISA | TRENTO | GRONINGEN | GLASGOW | RWTH | FRAUNHOFER | VICOMTECH | BEYOND-VISION | INTRACOM | 7BULLS | TELEFONICA | TRIALOG | ATC | LIV5G | IDSA | FORTH | AI INVEST | SWISS SMART | DEXAI | ITG | Koblenz | 8BELLS
T3.1 Goal-Driven Reasoning & Planning (M1–M30) | FORTH |  |  | 7.5 | 10 | [6 empty] | 10 | 1 | [5 empty] | 5 |  | 26 |  | 10 |  |  |  |  | 69.5
T3.2 Distributed Memory Management (M6–M36) | LBORO |  | 30 | [9 empty] | 1 | [7 empty] | 2 | [6 empty] | 33
T3.3 Continual & Federated Learning Mechanisms (M6–M42) | POLITO |  | 10 | 8 | [8 empty] | 1 |  |  | 15 | [6 empty] | 10 |  |  |  |  | 44
T3.4 Adaptive Behaviour & Self-Optimisation (M12–M42) | SSF |  |  | 14.5 | 8 | [7 empty] | 1 | [7 empty] | 1 |  | 20 |  |  |  |  | 44.5
|  | 0 | 40 | 30 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 15 | 0 | 0 | 5 | 0 | 29 | 0 | 40 | 0 | 0 | 0 | 0 | 191
WP4 – ICCO-Based Multi-Agent Self-Orchestration (M6–M48) | LBORO | LJMU | LBORO | OSLO | OULU | PISA | TRENTO | GRONINGEN | GLASGOW | RWTH | FRAUNHOFER | VICOMTECH | BEYOND-VISION | INTRACOM | 7BULLS | TELEFONICA | TRIALOG | ATC | LIV5G | IDSA | FORTH | AI INVEST | SWISS SMART | DEXAI | ITG | Koblenz | 8BELLS
T4.1 Interoperability Framework & Semantic Layer (M6–M30) | IDSA |  | 4 | 4 | [5 empty] | 3 |  | 10 | 2 | 1 |  |  | 9 |  |  | 14 | 2 |  |  |  | 3 |  |  | 52
T4.2 Modular Composability & Service Assembly Logic (M12–M36) | UiO |  | 6 | 24 | [8 empty] | 0.5 | 1 |  | 15 | 4 | [10 empty] | 50.5
T4.3 Dynamic Chaining & Workflow Execution Engine (M18–M42) | LBORO |  | 30 | 4 |  |  | 6 | [5 empty] | 0.5 | 2 | [6 empty] | 1 | [6 empty] | 43.5
T4.4 Decentralised Orchestration Algorithms (M24–M48) | UNITN |  | 6 | 16 | 18 |  | 30 | [5 empty] | 2 | 2 | 2 | 15 |  |  |  |  | 1 | [6 empty] | 92
|  | 0 | 46 | 48 | 18 | 0 | 36 | 0 | 0 | 3 | 0 | 10 | 5 | 6 | 2 | 30 | 13 | 0 | 0 | 14 | 4 | 0 | 0 | 0 | 3 | 0 | 0 | 238
WP5 – Trustworthiness, Safety & AI Act Compliance (M6–M54) | UoG | LJMU | LBORO | OSLO | OULU | PISA | TRENTO | GRONINGEN | GLASGOW | RWTH | FRAUNHOFER | VICOMTECH | BEYOND-VISION | INTRACOM | 7BULLS | TELEFONICA | TRIALOG | ATC | LIV5G | IDSA | FORTH | AI INVEST | SWISS SMART | DEXAI | ITG | Koblenz | 8BELLS
T5.1 Explainable AI Framework for Agentic & Federated Systems (M6–M42) | UPI |  |  |  |  | 30 |  |  | 3 |  | 5 |  | 2 | 3 |  |  | 5 |  |  |  | 4 | 3 | 3 | 2 |  | 5 |  | 65
T5.2 Responsible AI Governance Framework for Self-Orchestrating Foundries (M6–M48) | L5G | [7 empty] | 3 |  | 2 |  |  | 2 |  |  |  |  | 18 |  |  |  |  | 2 |  | 2 |  | 29
T5.3 AI Act-Conformant Explainability & Risk Mapping (M12–M54) | DEX |  |  |  |  | 5 |  |  | 3 |  | 5 |  |  | 0 |  |  |  | 10 | 1 |  | 2 |  |  | 38 |  | 5 |  | 69
T5.4 Fairness, Bias & Robustness Monitoring in Distributed Agentic Systems (M18–M54) | TID | [5 empty] | 6 |  | 3 |  | 5 |  |  | 0 |  | 15 | 1 |  | 1 |  |  |  |  | 2 |  | 5 |  | 38
T5.5 Transparency & Trust Metrics for Ecosystem-Level Validation (M30-M60) | UoG | [7 empty] | 38 |  | 5 |  |  | 0 |  |  | 1 | 10 | 1 |  | 2 |  |  | 2 |  | 5 |  | 64
T5.6 Security & Privacy Safeguards: Practice for security and privacy in Agentic AI | Trialog | [7 empty] | 3 |  | 7 |  |  | 3 | 3 |  | 10 |  | 1 |  | 2 |  |  | 2 |  | 7 |  | 38
|  | 0 | 0 | 0 | 0 | 35 | 6 | 0 | 53 | 0 | 29 | 0 | 2 | 8 | 3 | 15 | 17 | 20 | 22 | 0 | 10 | 3 | 3 | 48 | 0 | 29 | 0 | 303
WP6 – Self-Orchestrating AI Service Foundries & Ecosystem Enablement (M18–M60) | ICOM | LJMU | LBORO | OSLO | OULU | PISA | TRENTO | GRONINGEN | GLASGOW | RWTH | FRAUNHOFER | VICOMTECH | BEYOND-VISION | INTRACOM | 7BULLS | TELEFONICA | TRIALOG | ATC | LIV5G | IDSA | FORTH | AI INVEST | SWISS SMART | DEXAI | ITG | Koblenz | 8BELLS
T6.1 Foundry Core Lifecycle Infrastructure (M18–M48) | 7bulls |  |  | 3 |  |  |  |  | 1 |  |  |  |  | 2 | 15 |  |  | 9 |  |  | 3 | 2.5 |  |  |  |  | 1 | 36.5
T6.2 Agent Name Service (ANS) & Identity Infrastructure (M18–M48) | UoG | [7 empty] | 38 |  |  |  |  | 6 | [12 empty] | 1 | 45
T6.3 Marketplace & Discovery Interfaces (M24–M60) | ICOM | [12 empty] | 24 |  |  |  | 15 | [8 empty] | 1 | 40
T6.4 Federated Deployment & Runtime Optimisation (M30–M60) | UiO |  |  | 14 |  |  | 8 | [6 empty] | 8 | 2 |  |  | 15 |  |  |  |  | 8 |  |  |  | 1 | 56
T6.5 Testing and Validation | 8BELLS | [7 empty] | 2 |  |  |  |  | 8 | 5 | [5 empty] | 2 | 2.5 |  |  |  |  | 22 | 41.5
|  | 0 | 0 | 17 | 0 | 0 | 8 | 0 | 41 | 0 | 0 | 0 | 0 | 48 | 22 | 0 | 0 | 39 | 0 | 0 | 5 | 5 | 8 | 0 | 0 | 0 | 26 | 219
WP7 – ApplyAI Pilots, KPI Measurement & TRL Validation (M24–M60) | 7bulls | LJMU | LBORO | OSLO | OULU | PISA | TRENTO | GRONINGEN | GLASGOW | RWTH | FRAUNHOFER | VICOMTECH | BEYOND-VISION | INTRACOM | 7BULLS | TELEFONICA | TRIALOG | ATC | LIV5G | IDSA | FORTH | AI INVEST | SWISS SMART | DEXAI | ITG | Koblenz | 8BELLS
T7.1 Pilot 1 – Knowledge & Data-Driven Automation (M24–M60) | UOULU |  |  |  | 15 | 2 | [8 empty] | 1 |  |  |  | 1 |  | 10 |  |  | 2 |  |  |  | 31
T7.2 Pilot 2 – Industrial & Distributed Autonomous Systems (M30–M60) | VICOM |  |  |  |  | 2 |  |  |  | 12 |  | 30 |  |  | 1 |  |  |  | 1 |  |  |  | 20 | 2 |  |  |  | 68
T7.3 AI Agent Spaces - Cross-domain interoperability demonstration (M30-M60) | ITG |  |  |  |  | 2 | [6 empty] | 22 | 14 | 5 |  | 25 |  | 1 |  |  |  |  | 2 | 36 |  |  | 107
T7.4 Common Capabilities – Collaborative Agentic AI (AI Agent Spaces, User Feedback) | AII |  | 9 |  | 1 | [6 empty] | 1 | 4 | 5 | 7 |  |  |  | 1 |  | 2 | 15 |  | 2 | 2 |  |  | 49
T7.5 Federated Cross-Domain Integrated Pilot Demonstrations | L5G |  |  |  | 1 |  |  |  |  | 10 |  | 1 | 8 | 5 | 5 |  |  |  | 18 |  |  | 1 |  | 2 | 2 |  | 15 | 68
T7.6 KPI Framework, TRL Validation, User Feedback & Iterative Refinement (M30–M60) | 7bulls |  |  |  | 1 | [6 empty] | 1 | 8 | 5 | 15 |  |  |  | 1 |  |  | 7 |  |  | 4 |  | 3 | 45
|  | 0 | 9 | 0 | 18 | 6 | 0 | 0 | 0 | 22 | 0 | 33 | 42 | 29 | 34 | 0 | 25 | 0 | 23 | 0 | 12 | 23 | 20 | 10 | 44 | 0 | 18 | 368
WP8 – Dissemination, Exploitation, Standardisation & Policy (M1–M60) | ATC | LJMU | LBORO | OSLO | OULU | PISA | TRENTO | GRONINGEN | GLASGOW | RWTH | FRAUNHOFER | VICOMTECH | BEYOND-VISION | INTRACOM | 7BULLS | TELEFONICA | TRIALOG | ATC | LIV5G | IDSA | FORTH | AI INVEST | SWISS SMART | DEXAI | ITG | Koblenz | 8BELLS
T8.1 Scientific Dissemination & Communication (M1–M60) | ATC |  | 2 | 4 | 2.5 | 5 | 5 | 4 | 4 | 5 | 7 | 3 | 3 | 2 | 4 | 5 | 2 | 20 | 1 | 2 | 4 | 1 | 2 | 2 | 1 | 7 | 2 | 99.5
T8.2 Open Source & Developer Ecosystem (M12–M60) | 8BELLS |  | 1 | 2 | 0.5 |  |  |  | 2 | 2 | 5 | 1 | 1 | 1 | 4 | 2 | 2 |  | 1 | 6 | 2 |  |  |  |  | 5 | 15 | 52.5
T8.3 Exploitation & Sustainability Strategy (M24–M60) | 8BELLS |  | 1 |  | 0.5 |  |  |  | 0.5 |  | 5 |  | 1 | 4 | 6 | 4 | 1 | 5 | 1 |  |  | 1 |  |  | 1.5 | 5 | 15 | 51.5
T8.4 Standardisation & Policy Engagement (M12–M60) | IDSA |  | 1 |  | 0.5 |  |  |  | 0.5 |  | 7 |  | 0.5 | 1 |  | 1 | 9 |  | 1 | 10 | 2 |  |  | 2 | 0 | 7 |  | 42.5
|  | 0 | 5 | 6 | 4 | 5 | 5 | 4 | 7 | 7 | 24 | 4 | 5.5 | 8 | 14 | 12 | 14 | 25 | 4 | 18 | 8 | 2 | 2 | 4 | 2.5 | 24 | 32 | 246
|  | 0 | 110 | 113 | 62 | 59 | 68 | 58 | 104 | 80 | 86.5 | 74 | 79 | 114 | 90 | 85 | 93 | 94 | 56 | 35 | 75 | 51 | 78 | 78 | 80 | 86.5 | 80 | 1989

## Other direct cost
Other direct cost |  |  | note: most costs are other direct cost, including audit cost
total per partner
LJMU | 0
Loughborough | 92560
Oslo | 90960.8794
OULU | 104000
PISA | 79000
TRENTO | 65000
Groningen | 36000
Glasgow | 54000
RWTH | 144000
Fraunhofer | 94000 |  | 81200
Vicomtech | 79900
Beyond Vision | 90200
Intracom | 85700
7bulls | 44000
Telefonica | 101000
Trialog | 56000
ATC | 39000
Liv5G | 86000
IDSA | 64500
FORTH | 66800
AI Invest | 39000
Swiss Smart | 73000
DEXAI | 37500
ITG | 70400
Koblenz | 94000
8BELLS | 49000
1786520.8794
partner | cost type | cost | justification
LJMU | Travel | 0
| Travel | 0
Audit
Equipment etc.
Loughborough | Travel | 33000 | Essential project meetings
| Travel | 25000 | Travel for project dissemination at conferences/workshops
| Equipment | 28800 | Upgrade existing GPU cluster and edge compute testbed
| Consumables | 5760 | Laptops for project researchers (postdocs)
Oslo | Travel | 66000 | Plenary meetings, technical meetings, conferences, project reviews
| Travel | 0
|  | 8960.8794 | Advanced computers
|  | 16000 | Publication fees
OULU | Travel | 50000 | Project meetings (long distances from Finland)
| Travel | 24000 | Conferences, workshops and other relevant events
| Audit, publication fees | 5000 | Audit, publication fees, etc.
| Equipment etc. | 25000 | Equipment for real-life evaluations
PISA | Travel | 29000
| Travel | 25000
| Equipment | 25000 | Server for training and evaluating explainable and federated agents
TRENTO | Travel | 29000 | Project meetings
| Travel | 16000 | Conferences, workshops and other relevant dissemination and communication events. Planned participation in at least 4 conferences with an authored paper.
| Audit, publication fees | 5000 | Audit, publication fees for at least two open access journals, etc.
| Equipment | 15000 | Server to run and assess orchestration algorithms
Groningen | Travel | 30000
| Travel | 6000
Glasgow | Travel | 29000
| Travel | 25000
RWTH | Travel | 38000
| Travel | 6000
| Equipment | 100000 | Euqpiment Upgrade GAIA-Xperience Lab for Agentic Industrial Use Cases
Fraunhofer | Travel | 41000 | Project meetings
| Travel | 25000 | Travel for project dissemination at conferences/workshops; meetings of standardisation bodies (ISO, CEN/CENELEC)
| Audit, publication fees | 8000 | Audit, publication fees, etc.
| Equipment etc. | 20000 | Equipment for real-life evaluations
Vicomtech | Travel | 36300
| Travel | 6600 | Conferences, workshops and other relevant events
| Audit, publication fees | 15000 | Audit 3K + publication (2K*6=12K)
| Equipment etc. | 22000 | Equipment for pilot (18K for server for local LLM + 4K for tokens for cloud services)
Beyond Vision | Travel | 49200
| Travel | 3000
| Equipment | 18000 | 2 laptops (3000), sensors (15000)
| Consumables | 20000 | Electronic and mechanical parts for drones development
Intracom | Travel | 53200 | Project meetings
| Travel | 5000 | Conferences, workshops and other relevant events
| Equipment etc. | 20000 | Equipment for development testing and validation
| Publication fees | 3000
| Audit | 4500
7bulls | Travel | 35000 | Project meetings
| Travel | 5000 | Conferences
| Audit | 4000
Telefonica | Travel | 46000
| Travel | 30000
| Audit, publication fees | 5000
| Equipment | 20000
Trialog | Travel | 33000
| Travel | 16000
| Audit | 4000
| PUblication fees | 3000
ATC | Travel | 25000 | Project meetings
| Travel | 10000 | Attending Dissemination Events
| Audit, publication fees | 4000
Liv5G | Travel | 46000
| Travel | 0
| Hardware | 25000 | Computing
| Fees and charges | 15000 | Connectivity
IDSA | Travel | 34500 | Participation in 15 project meetings (€1500 p/p)
| Travel | 12000 | Participation to 4 large-scaled data space related events with a booth (EBDVF, Data Spaces Symposium, Data Sharing Festival) to disseminate project outcomes. (with two persons)
| Travel | 12000 | Participation to 4 conventions/meetings with standardization bodies (CEN/CENELEC, ISO, ETSI) - with two persons
| Audit, standardisation committes fees | 6000 | Audit, standarisation committes fees, etc.
FORTH | Travel | 39600
| Travel | 7200
|  | 20000 | Equipment for real-life evaluations/implementtations and computing infrastractures
AI Invest | Travel | 35000 | Project meetings
| Travel | 0
| Audit | 4000
Swiss Smart | Travel | 38000 | Project meetings
| Travel | 5000 | Conferences, workshops and other relevant events
| Audit, publication fees | 10000 | Audit
| Equipment etc. | 20000 | Equipment for real-life evaluations
DEXAI | Travel | 22500 | Project meetings (2/year) and liaison meetings (Cluster meetings)
| Travel | 15000 | and standardisation commitees (ISO, CEN-CENELEC), conferences and symposia
ITG | Travel | 22000 | Project meetings (6 meetings, 2 EC report meetings, 2 persons 1000 €/each); travels to fair and conferences (3, 2 persons, 1000 €/each)
| Equipment | 40000 | Depreciation costs of GPU units used to run the AI agents
|  | 2400 | Registration fees to conferences, workshops and other relevant events
|  | 3000 | Audit
|  | 3000 | Publication fees (1 open access peer-reviewed paper)
Koblenz | Travel | 41000 | Project meetings
| Travel | 25000 | Travel for project dissemination at conferences/workshops; meetings of standardisation bodies (ISO, CEN/CENELEC)
| Audit, publication fees | 8000 | Audit, publication fees, etc.
| Equipment etc. | 20000 | Equipment for real-life evaluations
8BELLS | Travel | 34000
| Travel | 0
| Audit, publication fees | 5000
| Equipment costs for the UAV platform ( i.e., FPGA, damages, thermal imaging system customization based on UC requirements) | 10000

## Subcontracting
subcontracting |  |  | NOTE rules for subcontracting: only if people are hired to do their normal work and are paid commercial rates
total per partner
LJMU | 0
Loughborough | 0
Oslo | 0
OULU | 60000
PISA | 0
TRENTO | 0
Groningen | 0
Glasgow | 0
RWTH | 0
Fraunhofer | 0
Vicomtech | 0
Beyond Vision | 0
Intracom | 0
7bulls | 0
Telefonica | 0
Trialog | 0
ATC | 0
Liv5G | 60000
IDSA | 0
FORTH | 0
AI Invest | 0
Swiss Smart | 0
DEXAI | 0
ITG | 0
Koblenz | 0
8bells | 0
120000
partner | Cost type | Cost | Justification
LJMU
Loughborough
Oslo
OULU | Test network & facilities | 60000 | The lease costs of the private 5G Hospital network for T7.1 evaluations, 20k€/y x3.
PISA
TRENTO
Groningen
Glasgow
RWTH
Fraunhofer
Vicomtech
Beyond Vision
Intracom
7bulls
Telefonica
Trialog
ATC
Liv5G | Test network lease | 60000 | 20k/yr for 3 years lab and venue
IDSA
FORTH
AI Invest
Swiss Smart
DEXAI
ITG
Koblenz
8bells

## Travel
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Meetings | Date | Location | LJMU | Loughborough | Oslo | OULU | PISA | TRENTO | Groningen | Glasgow | RWTH | Fraunhofer | Vicomtech | Beyond Vision | Intracom | 7bulls | Telefonica | Trialog | ATC | Liv5G | IDSA | FORTH | AI Invest | Swiss Smart | DEXAI | ITG | Koblenz | 8bells
Consortium meeting and liaison meeting (3/year) |  |  |  | 15 | 15 | 15 | 21 | 21 | 24 | 21 | 25 | 25 | 25 | 25 | 30 |  | 15 | 25 |  | 15 | 15 | 25 |  | 30 | 15 |  | 25
Review commission (3 total) |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 6 | 3 | 6 | 3 |  | 3 | 3 |  | 3 | 3 | 3 |  | 3 |  |  | 6
Bilateral (1/year) |  |  |  | 15 | 15 | 2 | 5 | 5 | 3 | 5 | 10 | 10 | 5 | 10 | 5 |  | 5 | 5 |  | 5 | 5 | 5 |  | 5 |  |  | 10
Total persons |  |  | 0 | 33 | 33 | 20 | 29 | 29 | 30 | 29 | 38 | 41 | 33 | 41 | 38 | 33 | 23 | 33 | 0 | 23 | 23 | 33 | 33 | 38 | 15 | 0 | 41 | 34
Average travel cost |  |  |  | 1000 | 2000 | 2500 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1100 | 1200 | 1400 | 1200 | 2000 | 1000 |  | 2000 | 1500 | 1200 |  | 1000 | 1500 |  | 1000 | 1000
Total |  |  | 0 | 33000 | 66000 | 50000 | 29000 | 29000 | 30000 | 29000 | 38000 | 41000 | 36300 | 49200 | 53200 | 39600 | 46000 | 33000 | 0 | 46000 | 34500 | 39600 | 0 | 38000 | 22500 | 0 | 41000 | 34000
Dissemination / Standardisation |  |  | LJMU | Loughborough | Oslo | OULU | PISA | TRENTO | Groningen | Glasgow | RWTH | Fraunhofer | Vicomtech | Beyond Vision | Intracom | 7bulls | Telefonica | Trialog | ATC | Liv5G | IDSA | FORTH | AI Invest | Swiss Smart | DEXAI | ITG | Koblenz | 8bells
Retained total persons |  |  |  | 10 |  | 8 | 10 | 8 | 6 | 10 | 3 | 10 | 6 | 2 |  |  | 10 | 16 |  |  | 16 | 6 |  | 5 | 5 |  | 10
Average travel cost |  |  |  | 2500 |  | 3000 | 2500 | 2000 | 1000 | 2500 | 2000 | 2500 | 1100 | 1500 |  |  | 3000 | 1000 |  |  | 1500 | 1200 |  | 1000 | 3000 |  | 2500
Total |  |  | 0 | 25000 | 0 | 24000 | 25000 | 16000 | 6000 | 25000 | 6000 | 25000 | 6600 | 3000 | 0 | 0 | 30000 | 16000 | 0 | 0 | 24000 | 7200 | 0 | 5000 | 15000 | 0 | 25000 | 0